## Sheet1
Oyster Reef Restoration Progress Dashboard
Tributary | Tributary Restoration Plan | Reef Construction and Seeding | Monitoring and Evaluation | Completed/Target Acreage (2016)
Harris Creek (Md.) | Complete | Complete | In Progress | 351/351
Little Choptank (Md.) | Complete | In Progress |  | 351/440
Manokin (Md.) | In Progress |  |  | TBD/441 (draft)
Tred Avon (Md.) | Complete | In Progress |  | 87/147
Upper St. Mary's (Md.) | Complete | In Progress |  | TBD/60
Great Wicomico (Va.) | In Progress | In Progress |  | TBD/TBD
Lafayette (Va.) | Complete | Complete | In Progress | 82/80
Lower York (Va.) | Complete | In Progress |  | 35/200
Lynnhaven (Va.) | Complete | In Progress |  | 105/152
Piankatank (Va.) | Complete | In Progress |  | 317/438