## Outcome Achievement
year |  | Miles Planted Per Year | [6 empty] | 900 miles/ yr Annual Target (CBP 2014 Agreement) | % achieved | Cumulative Miles Planted in Watershed since 2010 |  | 14,400-mile E.O. Outcome Goal (entire watershed; 2010-2025) | % E.O. Outcome goal achievement
| DE | MD | NY | PA | VA | WV | FED | All |  |  |  | Cumulative miles planted since 1996
1996 | Miles Planted Per Year MD: 8.5; Miles Planted Per Year VA: 1.9; Miles Planted Per Year FED: 0.3; Miles Planted Per Year All: 10.7 |  |  |  | 10.7 |  |  |  | DE | MD | NY | PA | VA | WV
1997 | Miles Planted Per Year MD: 47.3; Miles Planted Per Year VA: 15.7; Miles Planted Per Year FED: 5.1; Miles Planted Per Year All: 68.1 |  |  |  | 78.8 |  |  | 2016 | 0 | 25.7 | 34.4 | 579 | 28.4 | 9.9
1998 | Miles Planted Per Year MD: 90.1; Miles Planted Per Year VA: 54.7; Miles Planted Per Year FED: 10; Miles Planted Per Year All: 154.8 |  |  |  | 233.6 |  |  | 2017 | 0 | 12.8192 | 15.9135 | 17.4732 | 5.5865 | 4.3347
1999 | Miles Planted Per Year MD: 114.8; Miles Planted Per Year VA: 94.5; Miles Planted Per Year FED: 14.2; Miles Planted Per Year All: 223.5 |  |  |  | 457.1 |  |  | 2018 | 0.020198 | 25.7044 | 9.6578 | 103.1195 | 7.4161 | 12.1639
2000 | Miles Planted Per Year MD: 145.1; Miles Planted Per Year VA: 65.3; Miles Planted Per Year FED: 1.6; Miles Planted Per Year All: 212 |  |  |  | 669.1 |  |  | 2019 | 0.027383 | 28.5192 | 8.3723 | 40.1911 | 5.7443 | 0
2001 | Miles Planted Per Year MD: 257.8; Miles Planted Per Year VA: 260.3; Miles Planted Per Year FED: 1.9; Miles Planted Per Year All: 520 |  |  |  | 1189.1 |  |  | 2020 | 0.029423 | 30.1906 | 7.449 | 86.5507 | 20.0804 | 24.9044
2002 |  | 251.9 |  | 436 | 434 |  | 0.3 | 1122.2 |  |  |  | 2311.3
2003 | Miles Planted Per Year MD: 160.9; Miles Planted Per Year PA: 336; Miles Planted Per Year VA: 229.5; Miles Planted Per Year All: 726.4 |  |  |  | 3037.7
2004 | Miles Planted Per Year MD: 76.7; Miles Planted Per Year PA: 525; Miles Planted Per Year VA: 151.9; Miles Planted Per Year All: 753.6 |  |  |  | 3791.3
2005 | Miles Planted Per Year MD: 30.3; Miles Planted Per Year PA: 656; Miles Planted Per Year VA: 129; Miles Planted Per Year All: 815.3 |  |  |  | 4606.6
2006 | Miles Planted Per Year MD: 28.7; Miles Planted Per Year PA: 617; Miles Planted Per Year VA: 83.7; Miles Planted Per Year All: 729.4 |  |  |  | 5336
2007 | Miles Planted Per Year MD: 22; Miles Planted Per Year PA: 315; Miles Planted Per Year VA: 48; Miles Planted Per Year All: 385 |  |  |  | 5721
2008 | Miles Planted Per Year MD: 17.6; Miles Planted Per Year PA: 355; Miles Planted Per Year VA: 76.7; Miles Planted Per Year All: 449.3 |  |  |  | 6170.3
2009 | Miles Planted Per Year MD: 9.2; Miles Planted Per Year PA: 652.75; Miles Planted Per Year VA: 59.7; Miles Planted Per Year All: 721.65 |  |  |  | 6891.95
2010 | 11 | 27.6 | no data | 279 | 30.6 | 10.7 |  | 358.9 |  |  | 358.9 | 7250.85 | 14400 | 2.492%
2011 | 11 | 42.9 | no data | 166.2 | 27.9 | 2.6 |  | 250.6 |  |  | 609.5 | 7501.45 | 14400 | 4.233%
2012 | 11 | 15.7 | 21.8 | 170.7 | 63.2 | 13.4 |  | 295.8 |  |  | 905.3 | 7797.25 | 14400 | 6.287%
2013 | 11.5 | 15.9 | 31.3 | 138.7 | 38.3 | 4.7 |  | 240.4 |  |  | 1145.7 | 8037.65 | 14400 | 7.956%
2014 | 0 | 16.9 | 32.2 | 34 | 23.6 | 7.2 |  | 113.9 | 900 | 12.66% | 1259.6 | 8151.55 | 14400 | 8.747%
2015 | 0 | 15.4 | 28.7 | 6.4 | 9.1 | 4.6 |  | 64.2 | 900 | 7.133% | 1323.8 | 8215.75 | 14400 | 9.193%
2016 | 0 | 25.7 | 34.4 | 579 | 28.4 | 9.9 |  | 677.4 | 900 | 75.27% | 2001.2 | 8893.15 | 14400 | 13.9%
2017 | 0 | 12.8192 | 15.9135 | 17.4732 | 5.5865 | 4.3347 |  | 56.1271 | 900 | 6.236% | 2057.3271 | 8949.2771 | 14400 | 14.29%
2018 | 0.020198 | 25.7044 | 9.6578 | 103.1195 | 7.4161 | 12.1639 |  | 158.0617 | 900 | 17.56% | 2215.3888 | 9107.3388 | 14400 | 15.38%
2019 | 0.027383 | 28.5192 | 8.3723 | 40.1911 | 5.7443 | 0 |  | 82.827 | 900 | 9.203% | 2298.2158 | 9190.1658 | 14400 | 15.96%
2020 | 0.029423 | 30.1906 | 7.449 | 86.5507 | 20.0804 | 24.9044 |  | 169.2045 | 900 | 18.8% | 2467.4203 | 9359.3703 | 14400 | 17.13%
Change from last reporting year (miles) | DE: 2019-2020
DE | DE: 0.0020396
MD | DE: 1.6714
NY | DE: -0.92338
PA | DE: 46.3596
VA | DE: 14.3361
WV | DE: 24.9044

## 2020Progress-WIP3
| WIP3 Acres | Square Ft | Width (ft) | Length (ft) | Miles |  |  |  |  | 2018 Progress | 2019 Progress | 2020 Progress Acres | WIP3 Acres
DE | 691.7204 | 30131340.6633 | 100 | 301313.4066 | 57.067 |  |  |  | DE | 582.4523 | 540.6984 | 261.15 | 691.7204
MD | 19821.3801 | 863419317.7012 | 100 | 8634193.177 | 1635.2644 |  |  |  | MD | 17402.3337 | 17671.6156 | 17757.3461 | 19821.3801
NY | 8799.351 | 383299727.464 | 100 | 3832997.2746 | 725.9467 |  |  |  | NY | 3147.8062 | 3265.6561 | 3067.63 | 8799.351
PA | 96971.0407 | 4224058530.9301 | 100 | 42240585.3093 | 8000.1134 |  |  |  | PA | 18016.267 | 10064.034 | 9465.3827 | 96971.0407
VA | 58374.8842 | 2542809954.6063 | 100 | 25428099.5461 | 4815.9295 |  |  |  | VA | 4400.6057 | 3389.2039 | 3057.7317 | 58374.8842
WV | 5898.3299 | 256931250.6697 | 100 | 2569312.5067 | 486.6124 |  |  |  | WV | 3270.6199 | 3246.2409 | 3090.3952 | 5898.3299
| 190556.7062 |  |  | Total | 15720.9333 |  |  |  |  | *Progress #s come from official scenarios and do not include narrow buffers
*Note: Buffer goals were pulled from the WIP3 Official scenario using CAST 19. These acres do not include narrow forest buffers
| 2020 Progress Acres | Square Ft | Width (ft) | Length (ft) | Miles | Gap to reach WIP3 (acres) | Gap to reach WIP3 (miles) | Annual miles needed 2021-2025 to reach WIP3
DE | 261.15 | 11375693.9261 | 100 | 113756.9393 | 21.5449 | 430.5704 | 35.5221 | 7.1044
MD | 17757.3461 | 773509997.5776 | 100 | 7735099.9758 | 1464.9815 | 2064.034 | 170.2829 | 34.0566
NY | 3067.63 | 133625961.7535 | 100 | 1336259.6175 | 253.0796 | 5731.721 | 472.8671 | 94.5734
PA | 9465.3827 | 412312069.7703 | 100 | 4123120.6977 | 780.8943 | 87505.658 | 7219.2191 | 1443.8438
VA | 3057.7317 | 133194793.0518 | 100 | 1331947.9305 | 252.2629 | 55317.1525 | 4563.6665 | 912.7333
WV | 3090.3952 | 134617615.2641 | 100 | 1346176.1526 | 254.9577 | 2807.9347 | 231.6547 | 46.3309
| 36699.6357 |  |  | Total | 3027.7209 | 153857.0705 | 12693.2124 | 2538.6425
153857.0705
This is the 2020 Official Progress scenario (not the no expiration scenarios which are only used to calculate annual miles added)

## 2017-20 No Expiration Scenarios
New Reported Annual Acres/Loss | 2009-2010 | 2010-2011 | 2011-2012 | 2012-2013 | 2013-2014 | 2014-2015 | 2015-2016 | 2016-2017 | 2017-2018 | 2018-2019 | 2019-2020
DE | -1287.998 | 1288.001 | -0.004 | 0.003 | 267 | 0 | 0 | 0 | 0.24701 | 0.33488 | 0.35982
MD | -9161.774 | 10307.826 | 492.954 | 584.22 | 394 | 307 | 329 | 202 | 405.0392 | 449.3934 | 334.3188
NY | 343.326 | 219.782 | 132.897 | 133.321 | 193 | 373 | -21 | 224 | 135.9444 | 117.8499 | 71.21
PA | 18032.517 | 8051.105 | 1205.566 | -15149.671 | 3803 | 105 | -10929 | 223 | 1316.0545 | 512.9357 | 1104.5965
VA | 109.588 | 1734.643 | 806.455 | 299.902 | 36 | 109 | 136 | 132 | 175.2299 | 135.73 | 316.419
WV | 634.086 | 768.54 | 310.691 | 83.769 | 60 | 65 | 78 | 31 | 86.9901 | 0 | 178.1042
No Expiration Scenario Miles for 2017-2020
2017
| acres* | square feet | width (feet) | length (feet) | miles
DE | 2009-2010: 0; 2010-2011: 0; 2011-2012: 0; 2012-2013: 0; 2013-2014: 0
MD | 2009-2010: 202; 2010-2011: 8799120; 2011-2012: 130; 2012-2013: 67685.5385; 2013-2014: 12.8192
NY | 2009-2010: 224; 2010-2011: 9757440; 2011-2012: 116.128; 2012-2013: 84023.1469; 2013-2014: 15.9135
PA | 2009-2010: 223; 2010-2011: 9713880; 2011-2012: 105.29; 2012-2013: 92258.3341; 2013-2014: 17.4732
WV | 2009-2010: 31; 2010-2011: 1350360; 2011-2012: 59; 2012-2013: 22887.4576; 2013-2014: 4.3347; 2015-2016: Average 2017 width**
VA | 2009-2010: 132; 2010-2011: 5749920; 2011-2012: 194.9348; 2012-2013: 29496.6317; 2013-2014: 5.5865; 2015-2016: 100.8921
2018
| acres* | square feet | width (feet) | length (feet) | miles |  |  | State total miles
DE | 0.24701 | 10759.6934 | 100.8921 | 106.6455 | 0.020198 |  | DE | 0.020198
MD | 405.0392 | 17643507.332 | 130 | 135719.2872 | 25.7044 |  | MD | 25.7044
NY | 135.9444 | 5921737.9252 | 116.128 | 50993.1965 | 9.6578 |  | NY | 9.6578
PA | 1316.0545 | 57327332.1313 | 105.29 | 544470.8152 | 103.1195 |  | PA | 103.1195
VA | 175.2299 | 7633016.0736 | 194.9348 | 39156.7646 | 7.4161 |  | VA | 7.4161
WV | 86.9901 | 3789286.8665 | 59 | 64225.2011 | 12.1639 |  | WV | 12.1639
Total | 2013-2014: 158.0819
2019
| acres* | square feet | width (feet) | length (feet) | miles |  |  | State total miles
DE | 0.33488 | 14587.2838 | 100.8921 | 144.583 | 0.027383 |  | DE | 0.027383
MD | 449.3934 | 19575577.7954 | 130 | 150581.3677 | 28.5192 |  | MD | 28.5192
NY | 117.8499 | 5133543.1567 | 116.128 | 44205.9035 | 8.3723 |  | NY | 8.3723
PA | 512.9357 | 22343480.557 | 105.29 | 212208.952 | 40.1911 |  | PA | 40.1911
VA | 135.73 | 5912398.8 | 194.9348 | 30330.135 | 5.7443 |  | VA | 5.7443
WV | 0 | 0 | 59 | 0 | 0 |  | WV | 0
Total | 2013-2014: 82.8544
2020
| acres* | square feet | width*** (feet) | length (feet) | miles |  |  | State total miles
DE | 0.35982 | 15673.8202 | 100.8921 | 155.3523 | 0.029423 |  | DE | 0.029423
MD- urban | 107.3 | 4673988 | 50 | 93479.76 | 17.7045 | MD total | MD | 30.1906
MD- ag | 227.02 | 9888991.2 | 150 | 65926.608 | 12.4861 | 30.1906 | NY | 7.449
NY- urban | 1.21 | 52707.5856 | 35 | 1505.931 | 0.28521 | NY total | PA | 86.5507
NY- ag | 9.8 | 426888.1697 | 43 | 9927.6319 | 1.8802 | 7.449 | VA | 20.0804
NY- ag with exclusion fencing | 60.2 | 2622310.1708 | 94 | 27896.9167 | 5.2835 |  | WV | 24.9044
PA | 2009-2010: 1104.5965; 2010-2011: 48116224.8364; 2011-2012: 105.29; 2012-2013: 456987.6041; 2013-2014: 86.5507
VA | 2009-2010: 316.419; 2010-2011: 13783211.0355; 2011-2012: 130; 2012-2013: 106024.7003; 2013-2014: 20.0804
WV | 2009-2010: 178.1042; 2010-2011: 7758218.4749; 2011-2012: 59; 2012-2013: 131495.2284; 2013-2014: 24.9044
Total | 2013-2014: 169.2045
*These numbers are difference between this year and the previous year no expiration scenarios in CAST. For example, 2020 (acres) numbers are difference between the 2020 and 2019 no expiration scenarios in CAST
**Average 2017 buffer widths across jurisdictions used to estimate DE buffer widths from 2018 to present
***MD, NY and VA updated their average buffer width in 2020

## Notes
Miles of Riparian Forest Buffer Planted
Source: CBPO
Contact: Katherine Wares, CRC, Chesapeake Bay Program
updated October 2017
Year 2010 goal: 10,000 restored miles of riparian forested buffer since 1996 in MD, PA, VA.
Miles include those buffered by at least 35 feet of forest on one side of stream.
Miles count once the forest is planted
The forest planted can include trees with shrubs and grasses, however the canopy at maturity must be from trees. The species must be natives.
The buffer can be managed to encourage natural succession to woody species resulting in a mature canopy of trees 12 acres to a mile
*note - As of 2003, federal miles are no longer tracked separately and are included in respective states' reporting.
*note - Beginning in 2004, federal progress is captured in the state totals
*note - PA's 2004 #s include miles from previous year, but can not be apportioned at this time
*note - PA reported 436 cumulative miles from 2000-2002, but was not able to attribute them to any particular year. They were not able to confirm any miles planted from 1996-1999.
*note - federal miles for 1998, 1999, 2000 were revised in 2003, affecting totals
*note - MD annual miles for 1996-2002 were revised 1/7/05, affecting totals
*note - DE adjusted NEIEN past year progress data in 2014, which included new 267 acres (44.5 miles) for years 2010-2013; these were distributed across this years as a proxy until we get the actual annual data
*note - in 2014, New York and Delaware are 6acres/mile cause of 50ft width buffers
*note - As of 2003, federal miles are no longer tracked separately and are included in respective states' reporting.
*note- as of 2018 Progress, we transitioned to the Phase 6 model and verification issues resulted in negative progress in the model. We therefore started using "no expiration" scenarios to calculate the new miles added each year
Beginning in 2010, began tracking the Executive Order Outcome goal to plant
14,400 miles 2010-2025 throughout the entire watershed.
Changes in Goals and Targets
Year Range | Goal | Cumulative or Annual | Source | Applicable Jurisdictions
1996-2010 | 10000 | Cumulative | 2002 CBPO EC Forest Directive | MD, PA, VA
2010-2025 | 14400 | cumulative during this period | Executive Order | Watershed wide
2007-present | 900 | Annual | 2007 CBPO EC Forest Directive, EO, CBP 2014 Watershed Agreement | Watershed wide