## Restoration Progress
Tributary | State | Year of Establishment1 | Tributary Restoration Plan | Reef Construction and Seeding | Monitoring and Evaluation2 | Baseline Reef Acreage3 | Completed Acreage4 | Target Acreage | % Completed
Harris Creek | MD | 2012 | Complete | Complete | In Progress | 3 | 351 | 351 | 100%
Little Choptank River | MD | 2013 | Complete | In Progress | In Progress | 0 | 351 | 440 | 79.77%
Tred Avon River | MD | 2014 | Complete | In Progress | In Progress | 0 | 87 | 147 | 59.18%
Upper St. Mary's River | MD | 2018 | Complete | Not yet started | N/A | 35 | TBD | 60 | TBD
Manokin River | MD | 2019 | In Progress | Not yet started | N/A | TBD | TBD | 441 (draft) | TBD
Lafayette River | VA | 2014 | Complete | Complete | In Progress | 70 | 82 | 80 | 102.5%
Piankatank River | VA | 2014 | Complete | In Progress | In Progress | 203 | 317 | 438 | 72.37%
Lynnhaven River | VA | 2016 | Complete | In Progress | In Progress | 91 | 105 | 152 | 69.08%
Lower York | VA | 2017 | Complete | In Progress | N/A | 2 | 35 | 200 | 17.5%
Great Wicomico | VA | 2017 | In Progress | In Progress | N/A | TBD | TBD | TBD | N/A
1Year tributary was approved by the Fisheries Goal Implementation Team
2Monitoring and evaluation is conducted at 3- and 6- years for fully constructed tributaries (Harris Creek, Lafayette) and for those with ongoing construction that have 3-year old reefs (Little Choptank, Tred Avon, Piankatank, Lynnhaven).
3Considered restored prior to large-scale restoration (either naturally occurring or older restoration projects).
4As of end of the 2019 calendar year; includes both baseline acreage and acres restored under the 10 tributaries initiative.
Tributary | Completed Acreage by Year1
| 2018 | 2019
Harris Creek
Little Choptank River | 56 | 8
Tred Avon River | 3 | 3
Upper St. Mary's River
Manokin River
Lafayette River | 12
Piankatank River | 15 | 47
Lynnhaven River |  | 14
Lower York |  | 33
Great Wicomico
1Although restoration efforts have been in place since 2012, 2018 is the first year that annual acreage is available.

## Funding
Summary Funding1
Maryland | $57.02 million
Virginia | $5.17 million
1Represents in-water restoration cost totals spent by end of calendar year 2019 under the 10 tributaries initiative. Provided by the Maryland and Virginia Oyster Restoration Interagency Workgroups.
Tributary | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019
Harris Creek | 3730000 | 6500000 | 19290000 | 7520000 | 293000 | 707850 | 159979
Little Choptank River |  |  | 15480000 | 4170000 | 2830000 | 646370 | 2970000 | 1150000
Tred Avon River |  |  |  | 1430000 | 684000 | 2500000 | 645224 | 605000
Notes for Tributary-specific funding:
The workgroups have developed in-water restoration cost totals for each state (in summary funding table above), and in some years for each tributary, but the figures by tributary by year have not always been differentiated.
Some changes have been made over the years in how different agencies tabulate their expenses.
More recent numbers are more accurate; older years' figures do not necessarily reflect changes in how some agencies tabulated their expenses.
Expect to include St. Mary's and Manokin funding in the future - all MD tributaries rather than "Choptank Complex"