## Restoration Progress
Tributary | State | Year of Establishment1 | Tributary Restoration Plan | Reef Construction and Seeding | Monitoring and Evaluation2 | Baseline Reef Acreage3 | Completed Acreage4 | Target Acreage | % Completed
Harris Creek | MD | 2012 | Complete | Complete | In Progress | 3 | 351 | 351 | 100%
Little Choptank River5 | MD | 2013 | Complete | Complete | In Progress | 0 | 358 | 358 | 100%
Tred Avon River | MD | 2014 | Complete | In Progress | In Progress | 0 | 92 | 147 | 62.59%
Upper St. Mary's River | MD | 2018 | Complete | Not yet started | N/A | 35 | TBD | 60 | TBD
Manokin River | MD | 2019 | Complete | Not yet started | N/A | 20 | TBD | 441 | TBD
Lafayette River | VA | 2014 | Complete | Complete | In Progress | 70 | 82 | 80 | 102.5%
Piankatank River | VA | 2014 | Complete | In Progress | In Progress | 203 | 378 | 438 | 86.3%
Lynnhaven River | VA | 2016 | Complete | In Progress | In Progress | 89 7 | 105 | 152 | 69.08%
Lower York | VA | 2017 | Complete | In Progress | N/A | 2 | 48 | 200 | 24%
Great Wicomico | VA | 2017 | Complete | In Progress | N/A | 100 | TBD | 122 | TBD
Eastern Branch of the Elizabeth River6 | VA | 2020 | N/A | Complete | In Progress | 3 | 24 | 20 | 120%
1Year tributary was approved by the Fisheries Goal Implementation Team
2Monitoring and evaluation is conducted at 3 and again at 6 years after construction for fully constructed tributaries and for those with ongoing construction that have 3-year-old reefs.
3Considered restored prior to large-scale restoration (either naturally occurring or older restoration projects).
4As of end of the 2020 calendar year; includes both baseline acreage and acres restored under the 10 tributaries initiative.
5Little Choptank target was changed to 358 acres following discussions by the Maryland Interagency Oyster Restoration Workgroup. This target acreage still exceeds the thresholds set for a restored tributary as defined in the Oyster Metrics.
6The Eastern Branch of the Elizabeth River was added as an 11th "bonus" tributary by Virginia in September 2020.
7In 2012, 2.2 baseline acres were lost due to Hurricane Sandy, reducing the baseline reef acreage in Lynnhaven River from 91 to 89 acres
Tributary | Completed Acreage by Year1
| 2018 | 2019 | 2020
Harris Creek
Little Choptank River | 56 | 8 | 7
Tred Avon River | 3 | 3 | 5
Upper St. Mary's River
Manokin River
Lafayette River | 12
Piankatank River | 15 | 47 | 61
Lynnhaven River |  | 16 | 0
Lower York |  | 33 | 13
Great Wicomico
Eastern Branch of the Elizabeth River |  |  | 21
1Although restoration efforts have been in place since 2012, 2018 is the first year that annual acreage is available.

## Funding
Summary Funding1
Maryland | $58.5 million
Virginia | $6.44 million
1Represents in-water restoration cost totals spent by end of calendar year 2020 under the 10 tributaries initiative. Provided by the Maryland and Virginia Oyster Restoration Interagency Workgroups.
Tributary | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Harris Creek | 3730000 | 6500000 | 19290000 | 7520000 | 293000 | 707850 | 159979 |  | 502777
Little Choptank River |  |  | 15480000 | 4170000 | 2830000 | 646370 | 2970000 | 1150000 | 796448
Tred Avon River |  |  |  | 1430000 | 684000 | 2500000 | 645224 | 605000 | 184736
Notes for Tributary-specific funding:
The workgroups have developed in-water restoration cost totals for each state (in summary funding table above), and in some years for each tributary, but the figures by tributary by year have not always been differentiated.
Some changes have been made over the years in how different agencies tabulate their expenses.
More recent numbers are more accurate; older years' figures do not necessarily reflect changes in how some agencies tabulated their expenses.
Expect to include St. Mary's and Manokin funding in the future - all MD tributaries rather than "Choptank Complex"