## Restoration Progress
Tributary | State | Year of Establishment1 | Tributary Restoration Plan | Reef Construction and Seeding | Monitoring and Evaluation2 | Baseline Reef Acreage3 | Completed Acreage4,8, 14 | Target Acreage8,9 | % Completed
Harris Creek10 | MD | 2012 | Complete | Complete | Complete | 0 11 | 343 | 343 | 100%
Little Choptank River5 | MD | 2013 | Complete | Complete | In Progress | 7 13 | 358 | 358 | 100%
Tred Avon River | MD | 2014 | Complete | Complete | In Progress | 0 | 131 | 130 | 100.8%
Upper St. Mary's River | MD | 2018 | Complete | Complete | In Progress | 35 | 60 | 60 | 100%
Manokin River | MD | 2019 | Complete | In Progress | In Progress | 0 12 | 345 | 441 | 78.23%
Lafayette River | VA | 2014 | Complete | Complete | In Progress | 70 | 82 | 82 | 100%
Piankatank River | VA | 2014 | Complete | Complete | In Progress | 203 | 497 | 444 | 111.9%
Lynnhaven River | VA | 2016 | Complete | In Progress | In Progress | 89 7 | 126 | 152 | 82.89%
Lower York | VA | 2017 | Complete | Complete | In Progress | 2 | 204 | 200 | 102%
Great Wicomico | VA | 2017 | Complete | Complete | In Progress | 100 | 124 | 124 | 100%
Eastern Branch of the Elizabeth River6 | VA | 2020 | N/A | Complete | In Progress | 3 | 24 | 20 | 120%
1Year tributary was approved by the Fisheries Goal Implementation Team
2Monitoring and evaluation is conducted at 3 and again at 6 years after construction for fully constructed tributaries and for those with ongoing construction that have 3-year-old reefs.
3Considered restored prior to large-scale restoration (either naturally occurring or older restoration projects).
4As of end of the 2024 calendar year; includes both baseline acreage and acres restored under the 10 tributaries initiative.
5Little Choptank target was changed to 358 acres following discussions by the Maryland Interagency Oyster Restoration Workgroup. This target acreage still exceeds the thresholds set for a restored tributary as defined in the Oyster Metrics.
6The Eastern Branch of the Elizabeth River was added as an 11th "bonus" tributary by Virginia in September 2020.
7In 2012, 2.2 baseline acres were lost due to Hurricane Sandy, reducing the baseline reef acreage in Lynnhaven River from 91 to 89 acres
8In 2022, the Harris Creek target and completed acreage were changed from 351 to 348 to reflect an error in the Maryland workgroup's records
9In 2022, the planned goals for Lafayette, Piankatank, and Great Wicomico were changed to actual implemented goals; thus the target acreages were changed slightly.
10 Per monitoring, 5 acres of previously restored acres no longer met all success criteria six years after restoration, so the target was revised to 343. This is still above the threshold, so this tributary is still considered completed.
11 Baseline reef acreage was revised to 0 because when monitored at 3 years, it didn't meet the metrics and needed to be reseeded.
12 This was revised from 20 to 0 acres due to Maryland DNR's resurvey of these reefs.
13 Initial surveys in the Little Choptank River showed that extensive reef acreage met the Oyster Metrics success criteria, and therefore would not require restoration treatment. Later, more detailed surveys dropped this baseline reef amount to 2 acres.
14A one-acre site originally used as a research site was deemed to be a restored reef and added to the total for Tred Avon River in 2024.

## Restored Acres By Year
Tributary | Cumulative Completed Acreage
| 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024
Harris Creek2 | 350 | 351 | 351 | 351 | 351 | 348 | 348 | 343 | 343
Little Choptank River | 178 | 284 | 338.8 | 351 | 358 | 358 | 358 | 358 | 358
Tred Avon River | 35 | 80.8 | 83.8 | 87 | 92 | 130 | 130 | 130 | 131
Upper St. Mary's River | N/A | N/A | N/A | N/A | N/A | 49 | 60 | 60 | 60
Manokin River | N/A | N/A | N/A | N/A | N/A | 35 | 45 | 219 | 345
Lafayette River | 70.5 | 75 | 80 | 82 | 82 | 82 | 82 | 82 | 82
Piankatank River | 25 | 253 | 278 | 317 | 378 | 444 | 444 | 497 | 497
Lynnhaven River | 63 | 90.6 | 90.6 | 105 | 105 | 114 | 114 | 114 | 126
Lower York | N/A | N/A | N/A | 35 | 48 | 55 | 195 | 204 | 204
Great Wicomico1 | N/A | 61 | 61 | 61 | - | 124 | 124 | 124 | 124
Eastern Branch of the Elizabeth River | N/A | N/A | N/A | N/A | 24 | 24 | 24 | 24 | 24
1Reflects an update in baseline acreage to 100 acres in 2020
2The Maryland Workgroup identified an error in their record-keeping and the corrected total acreage goal is 348 acres.
3A one-acre site originally used as a research site was deemed to be a restored reef and added to the total for Tred Avon River in 2024.